## Sheet1
Sno | Phase / Activity | Sub-Activities | Timeline
1 | Requirement Analysis & Data Study | Collect loss run files from brokers/TPAs. | Month 1
Analyze variations in spreadsheet layouts.
Identify column name variations and claim fields.
Define standard claim schema.
Identify mandatory vs optional fields.
Document validation rules and edge cases.
Define integration output format (JSON/Duckcreek/Guide wire API).
2 | Data Ingestion Framework | Design file ingestion architecture. | Month 1
Build file upload interface.
Implement Excel/CSV validation checks.
Store files in processing directory/storage.
Capture metadata (file source, upload timestamp).
Implement file processing pipeline triggers.
3 | Spreadsheet Parsing Engine Development | Implement Excel and CSV readers. | Month 2
Detect tables across sheets.
Identify header rows dynamically.
Extract claim rows and columns.
Handle merged cells and irregular layouts.
Convert extracted tables into structured dataframe format.
Validate extracted data consistency.
4 | Schema Mapping Framework | Develop configurable column mapping system. | Month 2 – Month 3
Implement YAML/JSON based mapping rules.
Identify column synonyms across broker formats.
Map extracted columns to standardized claim schema.
Log unmapped fields for manual review.
Create mapping configuration management system.
5 | Data Normalization & Validation Engine | Standardize date formats. | Month 3
Convert currency values to numeric format.
Normalize claim status categories.
Remove special characters and formatting issues.
Handle missing/null values.
Implement validation checks for required fields.
Build rule-based data quality validation module.
6 | LLM-Assisted Interpretation | Identify unstructured fields like claim descriptions. | Month 4
Design prompts for claim summarization.
Extract structured insights from text fields.
Integrate LLM processing with the pipeline.
Validate outputs before final publishing.
7 | Human-in-the-Loop Review Interface | Develop UI for reviewing extracted claims. | Month 4 – Month 5
Display parsed tables and claim records.
Highlight uncertain or missing fields.
Enable manual corrections.
Capture audit logs of user edits.
Implement approval workflow before publishing.
8 | Output Generation & Standardization | Convert processed data into standardized claim records. | Month 5
Generate JSON outputs aligned with claim schema.
Implement schema validation checks.
Package claim records for downstream systems.
Enable batch export of processed files.
9 | Integration with Downstream Systems | Design integration architecture. | Month 5
Build APIs for data export.
Format payloads for Guidewire / Duck Creek integration.
Implement error handling and retry mechanisms.
Log integration transactions and failures.
10 | Monitoring & Metrics Framework | Implement extraction accuracy measurement. | Month 6
Track schema mapping success rate.
Monitor manual correction rates.
Measure processing time per file.
Build monitoring dashboards.
Store logs for performance analysis.
11 | Testing, Deployment & Optimization | Conduct end-to-end testing with multiple broker formats. | Month 6
Perform performance optimization.
Deploy system to production environment.
Prepare user documentation.
Conduct training for operations team.
Plan ongoing maintenance and enhancements.